## Story1
Site Story: The user requires a homepage that displays the latest art posts. The user wants to be able to toggle between the latest and favorite art posts of the day. If they are logged in, they should have the ability to upvote or un-upvote a post, as well as create and view events.
Task | Description | Passing Criteria | Dependent on | Priority | Assignee | Status | Comments
1 | A common navigation header to handle navigation should be developed early to implement on all pages for consistency. It should provide navigation to all main pages on the site (Latest posts, Favorite Posts, Events, Login/Signup, Account, Home) | click on selected page button should direct user to that page
2 | Homepage needs to be created. It should contain the common navigation header. It should provide general information about the site, its purpose and usage. | - Page exists - Page contains toggle button that displays latest posts or favorite posts of the day - Page provides button navigation to event creation data if user logged in - Page provides button navigation to allow user to create post data if user logged in |  | .
3 | Common posts GUI should be created and used to display posts in the same format. A post should display a username, userId, post name, postId. If logged in, the posts will also display content, upvote section, comment section. Each post should also contain a button that navigates to Word Frequency Breakdown page.
4 | Latest posts page needs to be created leveraging common posts GUI. It should contain the common navigation header. It should contain the posts sectioned by day sorted by most recent posts. |  | 3
5 | Favorite posts page needs to be created leveraging common posts GUI. It should contain the common navigation header. It should contain the posts sectioned by day, sorted by most upvotes. |  | 3
A Word Frequency Breakdown page needs to be created. It should display the username of the poster, the userId of the poster, the post name, post id, and a list of the words in the post with a corresponding number of its occurrences
6 | Events page need to be created. It should only be accessible if user is logged in. It should provide an area for the user to enter the following data: event name, eventId, event location, event time, participants list, attending/not attending toggle. It should provide an area to view events sorted by most recent events. Events location should implement search and filter
7 | A login/signup page needs to be created. It should allow the user to login or signup for the site. | [5 empty] | This is something I have to look more into implementing. Haven't done so. Can we use dumb username:password authentication? Leverage google authentication?
8 | Users API needs to be created. It should use mongoDB. It should create the following endpoints: GET allUsers, GET userByID, POST createUser, DELETE removeUser.
9 | Posts API needs to be created. It should use mongoDB. It should create the following endpoints: GET allPosts, GET postById, POST createPost, DELETE removePost
10 | Events API need to be created. It should use mongoDB. It should create the following endpoints: GET allEvents, GET eventById, POST createEvent, DELETE removeEvent

## Story2
- Website shall provide section for user to post text piece
- Post shall contain text, userId, username, Upvote userId List
- Website shall persist posts from the user
- Website shall allow users to upvote or un-upvote a post
- Website shall allow user to display favorite piece of the day (Most upvotes for the day)
- Website shall allow user to display most recent posts of the day
- Website shall allow user to create events
- Events shall contain location, time, optional banner image, attending participants
- Analysis of posts (word frequency breakdown)
- Implement search and filter for events location when upon user enter

## Sheet1
Feature | Task | Requires | * Note POST references the HTTP method, while Post/post refer to the content a user can create and view * Anything not required should be looked into last
Login | Design GUI | - section for user to enter username - section for user to enter password - login button to post data - main navigation link - navigation link to Registration page
Login | Authenticate in middleware | - Middleware to create and add user to session. - Middleware to check if user logged in, redirect to posts if so
Register | Design GUI | - section for user to enter username - section for user to enter password - section for user to enter confirmation password - register button to post data - main navigation link - navigation link to Registration page
Register | Add user to database | - Register button click should post data to /register route - /register POST route should validate and add user to database, if successful, return user to login page with success message. Otherwise return error message
Posts | Design GUI | - section to POST post - Should contain post title entry section - Should contain post content entry section - should contain post button -section to GET posts - Post should contain username, userid, date and time, post content, post title, number of upvotes for post, word breakdown button, comment section for post
Posts | Add post | - Submit post button click should POST data to posts route and update the database with post data
Posts | Update post upvotes | - POST updated post; adding/removing userID from post upvote userId list when user toggles checkbox | ***NOT REQUIREMENT
Posts | Remove post | *** Didn't put in requirements, add if time allows | ***NOT REQUIREMENT
Posts | View word frequency breakdown | - Displays word breakdown - Should just have a GET route to display posts breakdown
Events | Design GUI | - section to POST event - should contain fields to insert event event name, event location, date, time, description, upload button to upload banner image, and a create event button - section to GET events - should contain event event name, event location, date, time, description, banner image
Events | Add event | - POST route for events should validate event and add to database
Events | Update event | - POST route for events should validate event and add to database | ***NOT REQUIREMENT
Events | Remove event |  | ***NOT REQUIREMENT